## Intro
Product Backlog - list of all product features, product owner responsible for prioritizing
Sprint Backlog - the to do list for the sprint
Burndown Chart - chart that shows how much work remains in a sprint
Release Backlog - same as the product backlog, may involve one or more sprints
Estimating:
User Story - high level definition of what the customer wants to do 'As a (user), I want (function) so that (desired result)
Story Points - simple way to estimate a level of effort (relative scoring used - from 1 - 10, with 1 being easy and 10 being most difficult.
Business Value - each user story has in the Product Backlog has a business value assigned - typically H, M, L

## Product Backlog
Product Backlog
Complete the Product Backlog with data for each of the stories (components) of the project. Fields with calculated data are shaded in grey. For definitions of each data component, hover over the title.
Overall Project Estimates
| The data is calculated from the details below |  | Work Estimate for Sprint 1 | 0
|  |  | Work Estimate for Sprint 2 | 0
|  |  | Work Estimate for Sprint 3 | 0
|  |  | Work Estimate for Sprint 4 | 0
|  |  | Work Estimate for Sprint 5 | 0
|  |  | Work Estimate for Sprint 6 | 0
|  |  | Work Estimate for Sprints 7 and beyond | 151
| This data should be completed at the beginning of the current Sprint |  | Total Sprint Information
|  |  | Current Sprint: | 1
|  |  | Total User Story Hours | 0
|  |  | Total available hrs for the sprint: | 120
|  |  | Focus Factor | 0%
|  |  | Number of Resources in Sprint | 3
| This data should be updated daily to determine resource requirements to finish the current Sprint |  | Current Sprint In-Progress Details
|  |  | User Stories Hours Remaining | 25
|  |  | Work Hours Remaining | 24 | Assume 8 hours per day
|  |  | Difference: | -1
|  |  | Work Days Remaining in Sprint | 1
|  |  | Number of Days in Sprint | 5
Details | [5 empty] | Team | [6 empty] | Sprint 1 | Sprint 2 | Sprint 3 | Sprint 4 | Sprint 5 | Sprint 6 | Later
Epic | Sprint | User Story Role | User Story Name | Story Details | Acceptance Test Criteria | How to Demo | Tasks | Analyst / Prep work | Development Estimate | QA | Total User Story | Time Remaining
user account | 30 | product user | Create a user account for the 500 users to log in | As a product user, i can sign up a sercuity user account .so that i can login the application. | 1. the account should have a security sysytem to protect their acoount. 2.Account names should ensure that they cannot be re-registered, and passwords should be a valid combination of upper and lower case letters and Numbers. |  | 1. Develop a document for each user to fill in personal information. 2. Users can update their personal information at any time. 3. Each user account can directly contact their own sharing board | 5 | 35 | 10 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50
main system | 45 | product user | Create a handwrtting and translation for the user | As a product user, i can use the application to handwriting and translation the word and paragraph | 1.The system should be able to support writing by hand and then converting to text 2.The system should be able to translate Chinese and English 3.The system should be able to save the identified translated text in the history record |  | 1. Create a connection between the screen driver and the API interface to ensure that the handwriting recognition function can work. 2. Ensure that the handwriting recognition text can be recognized in the API, translated and then output to the screen. 3. Make sure the database can receive the translation notes and save them on shareboard. | 10 | 60 |  | 70 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 70
shareboard management | 25 | administrator | Administrators review content Shared by users | As an administrator, I want to review my notes after users share their translation so I can make sure they are appropriate. | 1. The administrator has the right to view the translation notes uploaded by users to the sharing board 2. The administrator has the right to block the user's account |  | 1. Create the administrator's account to operate the user's account. 2. Set administrator permissions on the sharing board to operate the Shared notes. | 5 | 24 | 2 | 31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31

## Sprint Example
Sprint Progress Tracking - An Example
This Tab enables the Scrum Master to track the progress of the Sprint relative to the Plan. Each day, enter the number of hours remaining in the Sprint. The graph compares the planned Sprint completion with the actual progress. The Ideal Line shows the progress that would be expected if the Sprint proceeds as planned. The Time Remaining line shows the actual progress for the Sprint. On any day, if the Time Remaining is above the Ideal Line, the project is running late. If this is a consistent and significant trend for more than two days, defer some stories to a later Sprint and record this change in the Project Information. Use the Blockers table to record non-Sprint activities that affected the Sprint. These should be used to improve estimates for later Sprints.
Enter Sprint Number | 4 |  | This example uses different data than that in the Product Backlog Example
week of the Sprint - assumes week sprints | Enter Total Hours Remaining | Ideal Line
0 | 126 | 126
1 | 115
2 | 115
3 | 115
4 | 98.2
5 | 92.6
6 | 90.6
7 | 14
8 | 14
9 | 0
10 | 0 | 0
Blockers | Hours Spent
Data Base | 8
Prod Issue
Meetings | 12
Sick
Slush | 3
Bug
TOTAL | 23